## stage_activities
208	1	12	PMO Upload	site validation	1	NULL	1	1	1	1		NULL
209	2	6	STS Assessment	site approval	2	1	1	2	1	1		NULL
210	3	7	STS Head Endorsement to RAM	site approval	3	NULL	1	3	1	1		NULL
211	4	10	Vendor Awarding by RAM	site approval	4	NULL	1	4	1	1		NULL
212	5	3	Vendor Acceptance of Endorsement	site validation	5	NULL	1	5	1	1		NULL
213	6	3	Vendor Agent Assignment	site validation	6	NULL	1	6	1	1		NULL
214	7	2	Check Search Ring Options	site search	7	NULL	2	7	2	1		NULL
215	8	2	Advance Site Hunting - Initial negotiation and Assessment of Property Docs	site search	8	NULL	7	8	2	1		NULL
216	9	2	Submit ASHR to Agile / Engineering for Initial assessment and approval	doc approval	9	NULL	7	9	2	1		NULL
217	10	8	Schedule for Survey from Agile JTTS	site search	10	NULL	7	10	2	1		NULL
218	11	2	Signing of Reps/Vendor should upload SSDS / NTP Signoff in Aquila	doc validation	11	NULL	1	11	2	1		NULL
219	12	8	Ram Verification / Approval of Docs	doc approval	12	NULL	1	12	2	1		NULL
220	13	2	Negotiation of Lease Terms & NTP Approval / Approval of Conceptual Drawing / Property docs	doc upload	13	NULL	21	13	3	1		NULL
221	14	10	Approval of Conceptual Drawing	doc upload	14	NULL	7	14	3	1		NULL
222	15	2	Upload to aquila	doc upload	15	NULL	1	15	3	1		NULL
223	16	10	Ram Verification / Approval of Docs	doc upload	16	NULL	1	16	3	1		NULL
224	17	2	Seg Plan / SI / Traverse (CAAP Reqmt)- Vendor	doc upload	17	NULL	7	17	4	1		NULL
225	18	2	Vendor Upload	doc upoad	18	NULL	1	18	4	1		NULL
226	19	8	ram verification	doc validation	19	NULL	1	19	4	1		NULL
227	20	2	Brgy Clearance / Vendor Upoload	doc upload	20	NULL	2	20	5	1		NULL
228	21	8	Ram for Validation / Approval	doc approval	21	NULL	1	21	5	1		NULL
229	22	2	Process LGU Requirements	doc upload	22	NULL	7	22	5	1		NULL
230	23	2	Actual National Permits if applicable	doc validation	23	NULL	92	23	5	1		NULL
231	24	2	DENR Docs if applicable	doc maker	24	NULL	365	24	5	1		NULL
232	25	2	Submit application forms and requirements to LGU Engineering for Building Permit	doc approval	25	NULL	7	25	5	1		NULL
233	26	2	Uploading of Docs	doc approval	26	NULL	1	26	5	1		NULL
234	27	8	Validation by RAM	doc validation	27	NULL	1	27	5	1		NULL
235	28	6	RTB Declaration	doc upload	28	NULL	1	28	6	1		NULL
236	29	2	Vendor Sends Draft Contract for SAM Legal Verification including all docs	doc validation	29	NULL	30	29	6	1		NULL
237	30	8	Legal Approval		30	NULL	4	30	6	1		NULL
238	31	2	Vendor gets Lessor Signature / Upload signed contract		31	NULL	4	31	7	1		NULL
239	32	2	Vendor Endorse for Lease Package		32	NULL	1	32	7	1		NULL